## Overall
Tasks | Efforts | Status
Before scope Change
BA | 40 | Done
UI Design | 60 | Done
Mobile Mockup | 28 | Done
Test | 24 | Done
Sub total |  |  | 152
After scope Change
UI Design | 50
Dev | 229
Testing | 180
Sub Total |  |  | 459
Total |  |  | 611

## Detail
Task | Effort | Resource | Status
Before project scope changed
Requirement | 40 | Leon Jin
UI design for iPad and tablet | 60 | Kevin Kong
Android platform research | 8 | Carl Yan
IOS Mockup(iPad) | 20 | Sam Shi
After scope change
Design
High Level Design | 16 | Matt Zhu
UI Design for web | 50 | Kevin Kong
Implement
Platform setup | 12 | Matt Zhu
Fundmental implement | 16 | Matt Zhu
Function Model
DR1.0 Login | 8 | Matt Zhu
DR2.0 Book a meeting Room | 28 | Angle Fu
DR3.01 Display Avaible meeting | 15 | Angle Fu
DR 3.02 Display All meeting info | 12 | Angle Fu
DR 3.03 Display all meeting room booked by myself | 12 | Angle Fu
DR 4.0 Find a meeting room by date and time | 16 | Angle Fu
DR 5.0 Meeting room usage report | 28 | Matt Zhu
DR 6.0 Maintain meeting room Info | 22 | Matt Zhu
CR fixing | 44 | Matt Zhu, Angle Fu
Testing
Test Design
Test cycle 1